## Sheet1
Week | Date | Person | Level Of Effort | Description | No. of Hours | Planned Activity | Actual Activity | Week | Date | Person | Level Of Effort | Description | No. of Hours | Planned Activity | Actual Activity
1(13 May-19 May) |  | YiXiu | - | Overseas | 0 | - | - | 1(13 May-19 May) | 13May2013 | Angela | 100% |  | 8 | LiftOff WorkShop | LiftOff WorkShop
1(13 May-19 May) |  | YiXiu | - | Overseas | 0 | - | - | 1(13 May-19 May) | 14May2013 | Angela | 100% |  | 8 | LiftOff WorkShop | LiftOff WorkShop
2(20 May-26 May) | 20May2013 | YiXiu | 100% | Reading through notes from Liftoff. Fact finding of jinja template. Trying out of GAE tutorials. | 7 | Learning about python,html and cathing up on Liftoff | Did tutorial for python and html. Read through given notes for Liftoff | 1(13 May-19 May) | 19May2013 | Angela | 100% | Fact-Finding: Learning syntax and code more of Python, HTML | 4 | Code Academy Tutorial | Code Academy Tutorial
2(20 May-26 May) | 21May2013 | YiXiu | 100% | Brainstorming of ideas,finalising main idea for website | 7 | Brainstorming of ideas and choosing the most approriate idea for our webpage. Rough sketch of design of webpage | Brainstorming of ideas and choosing the most approriate idea for our webpage. Rough sketch of design of webpage | 2(20 May-26 May) | 20May2013 | Angela | 100% | Fact-Finding: JInja 2 and revise stuffs taught in LiftOff WorkShop (day1 +day2) | 5 | Recap &Revise materials taught in the Liftoff Workshop | Recap &Revise materials taught in the Liftoff Workshop
2(20 May-26 May) | 23May2013 | YiXiu | 100% | Discussion on the suitable layouts | 4 | Mock Up slides | Mock Up slides | 2(20 May-26 May) | 21May2013 | Angela | 100% | Discussion of different ideas &Analyzing them. Choose the best idea. Think of some possible features and discuss the layout and features of the webpage. Watched the video about the instructions of the Project Log & Project Wiki. Setting up of google drive account and creating the Log and Wiki files in google drive. Discussed the agenda of the next meeting as well. | 7 | Discuss ideas and choose the most approriate idea for our webpage. Think of possible layout of the webpage | Discuss ideas and choose the most approriate idea for our webpage. Think of possible layout of the webpage
2(20 May-26 May) | 23May2013 | YiXiu | 100% | Video Making Process:Finding suitable software, recording repeatedly, preparing scripts for ignition and mockup. | 7 | Ignition and Mock Up video | Ignition and Mock Up video | 2(20 May-26 May) | 22May2013 | Angela | 100% | Fact-Finding: Learning syntax and code more of CSS & JavaScript | 6 | Code Academy Tutorial | Code Academy Tutorial
2(20 May-26 May) | 24May2013 | YiXiu | 100% | Edit report | 3 | Week 3 mockup Report | Week3 mockup Report | 2(20 May-26 May) | 23May2013 | Angela | 100% | Discussion on the suitable layouts | 4 | Mock Up Slides | Mock Up Slides
3(27 May-02 Jun) | 27May2013 | YiXiu | 100% | Explore git and learn git commands Learning css with w3school.com | 4 | Learn how to use git and css | Learn how to use git and css | 2(20 May-26 May) | 23May2013 | Angela | 100% | Video Making Process:Finding suitable software, recording repeatedly, preparing scripts for ignition and mockup. | 7 | Ignition and Mock Up video | Ignition and Mock Up video
3(27 May-02 Jun) | 2013-05-28 | YiXiu | 100% | Learning html with w3school.com | 5 | Learn html tags and code | Learn html tags and code | 2(20May-26May) | 26May2013 | Angela | 100% | Edit report | 1 | Week3 mockup report | Week3 mockup report
3(27 May-02 Jun) | 2013-05-29 | YiXiu | 100% | Learning python online and fact finding | 8 | Learn about webapp2 and how to link webpages | Learn about webapp2 and how to link webpages | 2(20May-26May) | 26May2013 | Angela | 100% | learning how to manage the github account and explore what could be done to the repo. | 2 | Github Learning process | Github Learning process
3(27 May-02 Jun) | 2013-06-01 | YiXiu | 100% | Creating html files for website and designing with twitter bootstrap | 5 | Create landing page and homepage | Create landing page and homepage | 3(27 May-02 Jun) | 27May2013 | Angela | 100% | Fact Finding:Javascript | 2 | code Academy Tutorial | Code Academy Tutorial
4(03 Jun-09 Jun) | 2013-06-04 | YiXiu | 100% | Creating html files for profile and addreview and editing main.py to link webpages | 3 | Create html files and link webpages | Create html files and link webpages |  |  | Angela
4(03 Jun-09 Jun) | 2013-06-07 | YiXiu | 100% | Reasearch on NUS open id | 5 | Learn how open id works | Learn how open id works |  |  | Angela
4(03 Jun-09 Jun) | 2013-06-08 | YiXiu | 100% | Editing main.py for attributes and research on open id | 6 | Create classes to store attributes and learn about open id | Create classes to store attributes and learn about open id |  |  | Angela
4(03 Jun-09 Jun) | 2013-06-09 | YiXiu | 100% | Editing main.py for open id | 5 | Make NUS open id work and create classes to store attributes | Make NUS open id work and create classes to store attributes |  |  | Angela
5(10 Jun-16 Jun) | 2013-06-10 | YiXiu | 100% | Research on gql and sql | 4 | Learn about gql commands | Learn about gql commands |  |  | Angela
5(10 Jun-16 Jun) | 2013-06-15 | YiXiu | 100% | Research on gql and using gql in main.py | 3 | Learn about gql and make gql queries in main.py | Learn about gql and make gql queries in main.py |  |  | Angela
6(17 Jun-23 Jun) | 2013-06-17 | YiXiu | 100% | Learning gql datastore and creating database | 3 | Learn about datastore and create database for users | Learn about datastore and create database for users |  |  | Angela
6(17 Jun-23 Jun) | 2013-06-18 | YiXiu | 100% | Create database for modules and link with html forms | 3 | Create database for modules and link with html forms | Create database for modules and link with html forms |  |  | Angela
6(17 Jun-23 Jun) | 2013-06-19 | YiXiu | 100% | Editing html files to display reviews and profile | 5 | Edit html files | Edit html files |  |  | Angela
7(24 Jun-30 Jun) | 2013-06-24 | YiXiu | 100% | Editing html files to display reviews and profile | 5 | Edit html files | Edit html files |  |  | Angela
7(24 Jun-30 Jun) | 2013-06-25 | YiXiu | 100% | Research on storing NUS modules | 5 | Research on json | Research on json |  |  | Angela
7(24 Jun-30 Jun) | 2013-06-26 | YiXiu | 100% | Create new class to count modules and display reviews | 3 | Edit main.py | Edit main.py
7(24 Jun-30 Jun) | 2013-06-27 | YiXiu | 100% | Edit report and record video for peer evaluation | 8 | Edit report and record video | Edit report and record video
7(24 Jun-30 Jun) |  | YiXiu | 100%
7(24 Jun-30 Jun) |  | YiXiu | 100%