## Sheet1
Week | Date | Person | Level Of Effort | Description | No. of Hours | Planned Activity | Actual Activity | Week | Date | Person | Level Of Effort | Description | No. of Hours | Planned Activity | Actual Activity
1(13 May-19 May) |  | YiXiu | - | Overseas | 0 | - | - | 1(13 May-19 May) | 13May2013 | Angela | 100% |  | 8 | LiftOff WorkShop | LiftOff WorkShop
1(13 May-19 May) |  | YiXiu | - | Overseas | 0 | - | - | 1(13 May-19 May) | 14May2013 | Angela | 100% |  | 8 | LiftOff WorkShop | LiftOff WorkShop
2(20 May-26 May) | 20May2013 | YiXiu | 100% | Reading through notes from Liftoff. Fact finding of jinja template. Trying out of GAE tutorials. | 7 | Learning about python,html and cathing up on Liftoff | Did tutorial for python and html. Read through given notes for Liftoff | 1(13 May-19 May) | 19May2013 | Angela | 100% | Fact-Finding: Learning syntax and code more of Python, HTML | 4 | Code Academy Tutorial | Code Academy Tutorial
2(20 May-26 May) | 21May2013 | YiXiu | 100% | Brainstorming of ideas,finalising main idea for website | 7 | Brainstorming of ideas and choosing the most approriate idea for our webpage. Rough sketch of design of webpage | Brainstorming of ideas and choosing the most approriate idea for our webpage. Rough sketch of design of webpage | 2(20 May-26 May) | 20May2013 | Angela | 100% | Fact-Finding: JInja 2 and revise stuffs taught in LiftOff WorkShop (day1 +day2) | 5 | Recap &Revise materials taught in the Liftoff Workshop | Recap &Revise materials taught in the Liftoff Workshop
2(20 May-26 May) | 23May2013 | YiXiu | 100% | Discussion on the suitable layouts | 4 | Mock Up slides | Mock Up slides | 2(20 May-26 May) | 21May2013 | Angela | 100% | Discussion of different ideas &Analyzing them. Choose the best idea. Think of some possible features and discuss the layout and features of the webpage. Watched the video about the instructions of the Project Log & Project Wiki. Setting up of google drive account and creating the Log and Wiki files in google drive. Discussed the agenda of the next meeting as well. | 7 | Discuss ideas and choose the most approriate idea for our webpage. Think of possible layout of the webpage | Discuss ideas and choose the most approriate idea for our webpage. Think of possible layout of the webpage
2(20 May-26 May) | 23May2013 | YiXiu | 100% | Video Making Process:Finding suitable software, recording repeatedly, preparing scripts for ignition and mockup. | 7 | Ignition and Mock Up video | Ignition and Mock Up video | 2(20 May-26 May) | 22May2013 | Angela | 100% | Fact-Finding: Learning syntax and code more of CSS & JavaScript | 6 | Code Academy Tutorial | Code Academy Tutorial
2(20 May-26 May) | 24May2013 | YiXiu | 100% | Edit report | 3 | Week 3 mockup Report | Week3 mockup Report | 2(20 May-26 May) | 23May2013 | Angela | 100% | Discussion on the suitable layouts | 4 | Mock Up Slides | Mock Up Slides
3(27 May-02 Jun) | 27May2013 | YiXiu | 100% | Explore git and learn git commands Learning css with w3school.com | 4 | Llearn how to use git and css | Learn how to use git and css | 2(20 May-26 May) | 23May2013 | Angela | 100% | Video Making Process:Finding suitable software, recording repeatedly, preparing scripts for ignition and mockup. | 7 | Ignition and Mock Up video | Ignition and Mock Up video
|  | YiXiu | [5 empty] | 2(20May-26May) | 26May2013 | Angela | 100% | Edit report | 1 | Week3 mockup report | Week3 mockup report
|  | YiXiu | [5 empty] | 2(20May-26May) | 26May2013 | Angela | 100% | learning how to manage the github account and explore what could be done to the repo. | 2 | Github Learning process | Github Learning process
|  | YiXiu | [5 empty] | 3(27 May-02 Jun) | 27May2013 | Angela | 100% | Fact Finding:Javascript | 2 | code Academy Tutorial | Code Academy Tutorial
|  | YiXiu | [7 empty] | Angela
|  | YiXiu | [7 empty] | Angela
|  | YiXiu | [7 empty] | Angela
|  | YiXiu | [7 empty] | Angela
|  | YiXiu | [7 empty] | Angela
|  | YiXiu | [7 empty] | Angela
|  | YiXiu | [7 empty] | Angela
|  | YiXiu | [7 empty] | Angela
|  | YiXiu | [7 empty] | Angela
|  | YiXiu | [7 empty] | Angela
|  | YiXiu | [7 empty] | Angela