## Sheet1
Week | Date | Person | Level Of Effort | Description | No. of Hours | Planned Activity | Actual Activity | Week | Date | Person | Level Of Effort | Description | No. of Hours | Planned Activity | Actual Activity
1(13 May-19 May) |  | YiXiu | - | Overseas | 0 | - | - | 1(13 May-19 May) | 13May2013 | Angela | 100% |  | 8 | LiftOff WorkShop | LiftOff WorkShop
1(13 May-19 May) |  | YiXiu | - | Overseas | 0 | - | - | 1(13 May-19 May) | 14May2013 | Angela | 100% |  | 8 | LiftOff WorkShop | LiftOff WorkShop
2(20 May-26 May) | 20May2013 | YiXiu | 100% | Reading through notes from Liftoff. Fact finding of jinja template. Trying out of GAE tutorials. | 7 | Learning about python,html and cathing up on Liftoff | Did tutorial for python and html. Read through given notes for Liftoff | 1(13 May-19 May) | 19May2013 | Angela | 100% | Fact-Finding: Learning syntax and code more of Python, HTML | 4 | Code Academy Tutorial | Code Academy Tutorial
2(20 May-26 May) | 21May2013 | YiXiu | 100% | Brainstorming of ideas,finalising main idea for website | 7 | Brainstorming of ideas and choosing the most approriate idea for our webpage. Rough sketch of design of webpage | Brainstorming of ideas and choosing the most approriate idea for our webpage. Rough sketch of design of webpage | 2(20 May-26 May) | 20May2013 | Angela | 100% | Fact-Finding: JInja 2 and revise stuffs taught in LiftOff WorkShop (day1 +day2) | 5 | Recap &Revise materials taught in the Liftoff Workshop | Recap &Revise materials taught in the Liftoff Workshop
2(20 May-26 May) | 23May2013 | YiXiu | 100% | Discussion on the suitable layouts | 4 | Mock Up slides | Mock Up slides | 2(20 May-26 May) | 21May2013 | Angela | 100% | Discussion of different ideas &Analyzing them. Choose the best idea. Think of some possible features and discuss the layout and features of the webpage. Watched the video about the instructions of the Project Log & Project Wiki. Setting up of google drive account and creating the Log and Wiki files in google drive. Discussed the agenda of the next meeting as well. | 7 | Discuss ideas and choose the most approriate idea for our webpage. Think of possible layout of the webpage | Discuss ideas and choose the most approriate idea for our webpage. Think of possible layout of the webpage
2(20 May-26 May) | 23May2013 | YiXiu | 100% | Video Making Process:Finding suitable software, recording repeatedly, preparing scripts for ignition and mockup. | 7 | Ignition and Mock Up video | Ignition and Mock Up video | 2(20 May-26 May) | 22May2013 | Angela | 100% | Fact-Finding: Learning syntax and code more of CSS & JavaScript | 6 | Code Academy Tutorial | Code Academy Tutorial
2(20 May-26 May) | 24May2013 | YiXiu | 100% | Edit report | 3 | Week 3 mockup Report | Week3 mockup Report | 2(20 May-26 May) | 23May2013 | Angela | 100% | Discussion on the suitable layouts | 4 | Mock Up Slides | Mock Up Slides
3(27 May-02 Jun) | 27May2013 | YiXiu | 100% | Explore git and learn git commands Learning css with w3school.com | 4 | Learn how to use git and css | Learn how to use git and css | 2(20 May-26 May) | 23May2013 | Angela | 100% | Video Making Process:Finding suitable software, recording repeatedly, preparing scripts for ignition and mockup. | 7 | Ignition and Mock Up video | Ignition and Mock Up video
3(27 May-02 Jun) | 2013-05-28 | YiXiu | 100% | Learning html with w3school.com | 5 | Learn html tags and code | Learn html tags and code | 2(20May-26May) | 26May2013 | Angela | 100% | Edit report | 1 | Week3 mockup report | Week3 mockup report
3(27 May-02 Jun) | 2013-05-29 | YiXiu | 100% | Learning python online and fact finding | 8 | Learn about webapp2 and how to link webpages | Learn about webapp2 and how to link webpages | 2(20May-26May) | 26May2013 | Angela | 100% | learning how to manage the github account and explore what could be done to the repo. | 2 | Github Learning process | Github Learning process
3(27 May-02 Jun) | 2013-06-01 | YiXiu | 100% | Creating html files for website and designing with twitter bootstrap | 5 | Create landing page and homepage | Create landing page and homepage | 3(27 May-02 Jun) | 27May2013 | Angela | 100% | Fact Finding:Javascript | 2 | code Academy Tutorial | Code Academy Tutorial
4(03 Jun-09 Jun) | 2013-06-04 | YiXiu | 100% | Creating html files for profile and addreview and editing main.py to link webpages | 3 | Create html files and link webpages | Create html files and link webpages | 3(27 May-02 Jun) | 5/31/2013 | Angela | 100% | Peer evaluation | 3 | Peer evaluation | Peer evaluation
4(03 Jun-09 Jun) | 2013-06-07 | YiXiu | 100% | Reasearch on NUS open id | 5 | Learn how open id works | Learn how open id works | 3(27 May-02 Jun) | 5/31/2013 | Angela | 100% | Coding | 2 | Coding | Coding
4(03 Jun-09 Jun) | 2013-06-08 | YiXiu | 100% | Editing main.py for attributes and research on open id | 6 | Create classes to store attributes and learn about open id | Create classes to store attributes and learn about open id | 3(27 May-02 Jun) | 2013-01-06 | Angela | 100% | Exploring different buttons, icons and other properties of html file | 3 | Design of frontuser html & editting other html files | Design of frontuser html & editting other html files
4(03 Jun-09 Jun) | 2013-06-09 | YiXiu | 100% | Editing main.py for open id | 5 | Make NUS open id work and create classes to store attributes | Make NUS open id work and create classes to store attributes | 4(03 May-10 Jun) | 2013-03-06 | Angela | 100% | Exploring SQL functions | 2 | SQL | SQL
5(10 Jun-16 Jun) | 2013-06-10 | YiXiu | 100% | Research on gql and sql | 4 | Learn about gql commands | Learn about gql commands | 4(03 May-10 Jun) | 2013-04-06 | Angela | 100% | NUS open ID | 4 | learning code | learning code
5(10 Jun-16 Jun) | 2013-06-15 | YiXiu | 100% | Research on gql and using gql in main.py | 3 | Learn about gql and make gql queries in main.py | Learn about gql and make gql queries in main.py | 4(03 May-10 Jun) | 2013-05-06 | Angela | 100% | NUS open ID | 4 | Debugging | Debugging
6(17 Jun-23 Jun) | 2013-06-17 | YiXiu | 100% | Learning gql datastore and creating database | 3 | Learn about datastore and create database for users | Learn about datastore and create database for users | 4(03 May-10 Jun) | 2013-11-06 | Angela | 100% | Mission Control | 2 | Security, Cache, Sessions, Cookies | Security, Cache, Sessions, Cookies
6(17 Jun-23 Jun) | 2013-06-18 | YiXiu | 100% | Create database for modules and link with html forms | 3 | Create database for modules and link with html forms | Create database for modules and link with html forms | 5(10 Jun -16 Jun) | 2013-12-06 | Angela | 100% | Research on gql +sql | 8 | tutorial for the use of command lines | tutorial for the use of command lines
6(17 Jun-23 Jun) | 2013-06-19 | YiXiu | 100% | Editing html files to display reviews and profile | 5 | Edit html files | Edit html files | 5(10 Jun -16 Jun) | 6/14/2013 | Angela | 100% | read up on datastore +database of GAE | 5 | read up +practice | read up +practice
7(24 Jun-30 Jun) | 2013-06-24 | YiXiu | 100% | Editing html files to display reviews and profile | 5 | Edit html files | Edit html files | 6(17 Jun- 23 Jun) | 6/17/2013 | Angela | 100% | HTML+python files profile,changeprofile | 5 | created html +editting work | created html +editting work
7(24 Jun-30 Jun) | 2013-06-25 | YiXiu | 100% | Research on storing NUS modules | 5 | Research on json | Research on json | 6(17 Jun- 23 Jun) | 6/18/2013 | Angela | 100% | Database for moduleReviews | 5 | Debuggin for errors, as couldn’t be displayed | Debuggin for errors, as couldn’t be displayed
7(24 Jun-30 Jun) | 2013-06-26 | YiXiu | 100% | Create new class to count modules and display reviews | 3 | Edit main.py | Edit main.py | 6(17 Jun- 23 Jun) | 6/19/2013 | Angela | 100% | HTML files addReview viewReview | 3 | created html +editting work | created html +editting work
7(24 Jun-30 Jun) | 2013-06-27 | YiXiu | 100% | Edit report and record video for peer evaluation | 8 | Edit report and record video | Edit report and record video | 6(17 Jun- 23 Jun) | 6/20/2013 | Angela | 100% | HTML +python files Search, Searchfaculty, Searchfass | 4 | created html +editting work | created html +editting work
7(24 Jun-30 Jun) |  | YiXiu | 100% |  |  |  |  | 6(17 Jun- 23 Jun) | 6/22/2013 | Angela | 100% | added in the modules of FASS in html file as display | 5 | editing fass html | editing fass html
7(24 Jun-30 Jun) |  | YiXiu | 100% |  |  |  |  | 7(24 Jun- 30 Jun) | 6/25/2013 | Angela | 100% | Research on how to retrieve module details from CORS& JSON | 6 | research(askbot+json) | research(askbot+json)
[8 empty] | 7(24 Jun- 30 Jun) | 6/26/2013 | Angela | 100% | Added a construction html file + in python file | 1 | Added a construction html file + in python file | Added a construction html file + in python file
[8 empty] | 7(24 Jun- 30 Jun) | 6/27/2013 | Angela | 100% | Edit the whole folder before deployment | 2 | removed some unwanted codes and tried adding new codes in | removed some unwanted codes and tried adding new codes in
[8 empty] | 7(24 Jun- 30 Jun) | 6/27/2013 | Angela | 100% | Edit report &record video for peer evaluation | 7 | edit report and record video | edit report and record video